WINS LIP

Belonging Working Group – Activity Plan (2025–2028)

Purpose

### To guide the Belonging Working Group in coordinating small, practical actions that connect existing efforts, promote inclusive practices, and encourage collaboration—using available resources and partnerships to strengthen a sense of belonging in New Westminster.

### Focus Areas (2025–2028)

.

### Key Deliverables

Belonging Working Group – Work Plan (2025–2028)

| Year | Activities | Lead / Partners | Expected Outcomes | Deadline |
| --- | --- | --- | --- | --- |
| Year 1 (2025–2026) | Align local actions with Tamarack initiatives (partners share 2–3 activities that fit Tamarack themes). | BWG members | Short list of aligned initiatives; stronger connection to Tamarack strategy. | Feb-26 |
|  | Support Tamarack-led belonging events (promotion and participation). | Natalie + BWG members | Increased attendance and diversity at Tamarack events. | Ongoing |
| Year 2 (2026–2027) | Launch Newcomer Appreciation Campaign (10 profiles shared via social media and partner channels). | BWG members | Positive narratives shared; at least 10 profiles posted and cross-shared. One once a mont starting in April | Apr-26 |
|  | Belonging Exercise that will also provide data for Visual Mapping, | BWG members+ Community Connectors | At least 15 contributions gathered; summary report with insights and improvement ideas. | Apr-26 |
|  | Expand Welcoming Space Assessments (invite businesses/public spaces to self-assess using adapted checklist). | BWG members + EWG members | 10 new spaces complete self-assessment; 4 improvements implemented. | Dec-26 |
|  | Host 3 intergenerational dialogues (youth and seniors) and collect stories. (We could use intergenerational Mother Goose if created) | BWG members | 10 stories collected; visual display created. | Mar-27 |
| Year 3 (2027–2028) | Develop and share a “Belonging Practices Guide” based on lessons learned. | BWG members | Guide distributed to 20 organizations; adoption of inclusive practices. | Mar-28 |
|  | If appropiate continue with Newcomer Appreciation Campaign with broader partner involvement. | BWG members | 20 profiles shared; increased partner engagement. | Ongoing |
|  | Launch recognition program for “Belonging Champions” (businesses and organizations). | BWG members | At least 10 organizations recognized for welcoming practices. | Winter 2028 |
|  | Conduct light evaluation of BWG activities and impact. | BWG members | Online evaluation report completed; recommendations for next cycle. | Mar-28 |

### Ongoing Commitments related to this Activity Plan.

- Maintain at least five meetings per fiscal year (online or in person).

- WINS LIP Coordinator schedules meetings, circulates notes, and tracks progress.

- Share updates and opportunities via Teams or email.

- Keep coordination simple and focused on actions that bring clear value to members

- Rotating chair model; Cheryl until mid-Jan 2026.

- Shared Teams folder for documentation.

- Monitor number of initiatives mapped, profiles shared, spaces assessed, and stories collected.