WINS LIP

Employment Working Group – Activity Plan (2025–2028)

3-Year Plan Draft (For Review and Approval)

Purpose
To strengthen collaboration among employment partners in New Westminster, improve coordination of employment supports, and increase equitable access to fair and inclusive job opportunities for newcomers..

### Focus Areas (2025–2028)

### Key Deliverables

### Ongoing Commitments related to this Activity Plan.

- Maintain at least five meetings per fiscal year, with flexible online participation.

- WINS LIP Coordinator will schedule meetings, circulate notes, and track progress.

- Keep coordination simple and purpose-driven — focusing on activities that bring clear value to all members.

- Share program updates, events, and opportunities for collaboration via Teams or group email.

- Collaborate with the Chamber of Commerce and other community partners (possibly unions) to strengthen employer connections.

Employment Working Group - Work Plan (2025–2028)

| Year | Activities | Lead / Partners | Expected Outcomes | Deadline |
| --- | --- | --- | --- | --- |
| Year 1 (2025–2026) | Develop simple local inventory of employment services in New Westminster (include eligibility by immigration status). | WINS LIP Coordinator and WorkBC (Lead) | WINS LIP partners have a clear directory of services. | Mar-26 |
|  | Obtain existing resources to avoid duplication with WorkBC and other resources Simple Inventory of Employment Services, New Westminster – Fill out form | WorkBC, WINS LIP Coordinator |  | Mar-26 |
|  | Begin outreach to local businesses to introduce inventory and encourage inclusive hiring. | EWG members | Initial engagement with businesses on inclusive hiring (at least 5 new involved). |  |
|  | Identify sources of funding and collaboration (ongoing) | WINS LIP Coordinator, EWG members | Funding options identified | Ongoing |
| Year 2 (2026–2027) | Host Resume Feedback Clinic during New to New West Resource Fair (last week of May). | EWG members | Resume clinic delivered successfully. Newcomers gain practical resume support (at least 20% of participants in the event) | May-26 |
|  | Identify 3–4 co-host organizations . | Co-host organizations: Work BC, Douglas College, PIRS, ISSofBC |  |  |
|  | Backup volunteers | Career Development Practitioner programs | Volunteer support secured | May-27 |
|  | Deliver Workers’ Rights & Employment Awareness Workshop (two sessions: service providers online, clients in person with translation) |  | 80% of workshop participants report increased knowledge of workers’ rights in post-event evaluations. | Fall-26 |
|  | BC Federation of Labour, Justice Education Society (JES),, invite Legal Aid for Q&A |  |  |  |
|  | Begin developing employer-focused materials (information sheet or guide) | WINS LIP Coordinator, EWG members | Draft employer guide prepared | Winter-27 |
|  | Share finished inventory widely through Chamber of Commerce and city channels | WINS LIP Coordinator, Chamber of Commerce | Inventory shared publicly | Fall-26 |
| Year 3 (2027–2028) | Develop and distribute Employer Resource Infographic with inclusive hiring tools. | EWG members | Employer guide distributed to 30 employers. | Mar-28 |
|  | Launch Employer Award Program(gold/silver/bronze). | WINS LIP table | At least 5 employers adopt or show interest in inclusive practices. |  |
|  | Strengthen partnerships with Immigrant Employment Council of BC and Chamber of Commerce. | Chamber of Commerce, EWG members | Partnership agreements confirmed | Ongoing |
|  | Conduct light evaluation . | WINS LIP Coordinator, EWG members | online evaluation report completed | Mar-28 |

My notes

- Confirm WorkBC as lead for Inventory of Employment Services.

- Identify 3–4 organizations to co-host Resume Clinic.

- Discuss funding: Can organizations contribute from current streams? No?, what external funding should WINS LIP pursue?

- Agree tasks (confirm roles and funding list).

- Ask who and how we are going to present approved plan to WINS LIP table and ask for further collaboration.